## Sheet1
skill | complexity | task_name | subtask_name | Development/Programming | UI | QA | Total | Assumptions/Comments
4 | 2 | Membership | Integrating membership model | 3 | 0 | 0 | 3
4 | 2 | Membership | Integrating payment option along with membership | 4 | 1 | 1 | 6
3 | 1 | Membership | Free trial | 6 | 2 | 1 | 9
3 | 1 | Membership option | Member Search Preferrence Form | 3 | 2 | 1 | 6
3 | 1 | Membership option | Membership Type Selection/Edit form | 3 | 2 | 1 | 6
3 | 2 | Membership option | Sending search result via email | 6 | 1 | 2 | 9
3 | 2 | Membership option | Stop sending search results - if payment is failed. | 4 | 0 | 1 | 5
2 | 0 | Minor Updates | Replace the "Start Time" column with "City". | 0.5 | 0 | 0 | 0.5
2 | 0 | Minor Updates | Open "Book Race" or "Course Map" in new tab | 0 | 0 | 0 | 0
2 | 0 | Minor Updates | Change message on broken links. | 1 | 1 | 0.5 | 2.5
|  | TOTAL |  | 30.5 | 9 | 7.5 | 47 | hours
[7 empty] | 6 | days
Matt follow up questions
|  |  |  | Why does the free trial option add so much additional time? |  |  |  | Because we have to apply checks and do programming to stop user when trail period is end. And then if user pays system resume functioning again.
|  |  |  | What would the total hours estimate be if we drop the free trial option? (I could offer some sort of free product to new registrants instead) |  |  |  | Estimate will be reduce 9-10 hours, (total will be 36 after minus) but I recommend to do that. It will help you get more customer attracted to your product.
|  |  |  | What payment processing service would be used? Are there ongoing fees / costs associated with those services? |  |  |  | We are planning to use Stripe. It will cost "2.9% + 30¢ per successful card charge".
|  |  |  | Could emails be sent using my current email service provider? (GetResponse) |  |  |  | No it will be sent from our program using email programing without using GetResponse
|  |  |  | Would we be able to setup a test environment for the membership option / emails before going live? I would invite 10-20 people to participate in testing period. |  |  |  | Yes please buy another server on Heroku to setup test environment i.e. separate test site later where we can also do all the testing of new features on this site before going live.
|  |  |  | Probably a dumb question - but the hours above include all of the integration necessary between our existing database and the preference form |  |  |  | Yes