## Final Submission
skill | complexity | task_name | subtask_name | Development/Programming | UI Task | QA | Total | Assumptions/Comments
3 | 0 | Environment / Drupal Setup / Git Setup (Gitlab or Github) |  | 4 | 0 | 0 | 4 | Drupal setup, setting up git client which client will provide and then we will create branches (Develop, Staging, Sprint/Phase branch and developers own branch). Then all dev and frontend team will connect with git.
3 | 0 | User Signup | Creating user roles | 1 | 0 | 0 | 1
2 | 1 | User Signup | User registration form and creating fields | 6 | 3 | 1 | 10 | There are no exact field defined in requirement document. So we will add default fields and then client will explain or add himself from admin panel. This will automcally reduce or increase depending on client communication during development process. This estimate also depends how theme and frontend is build.
3 | 2 | User Signup | Exposing role for user and managing questions with respect to roles | 7 | 3 | 2 | 12 | Here again will create backend with dummy questions/fields and client will then add/edit accordingly. This will automcally reduce or increase depending on client communication during development process. This estimate also depends how theme and frontend is build
3 | 1 | User Signup | Retaining registration form data and other constraint | 8 | 0 | 1 | 9
2 | 1 | User Signup | User Private documents encryption (document used for authentication) | 6 | 0 | 1 | 7 | As you said you will provide more details on encryption in CLARIFICATION section under TECHNICAL question
3 | 1 | User Signup | Login process + Forgot Password + Complete authentication (There will be other screens like forgot password) | 3 | 3 | 1 | 7 | User will be by default disable and after verification process (which is out of the scoe of project) by admin will approve/enable/activate user within system.
2 | 0 | User Profile & Membership | User profile + Content permissions | 4 | 0 | 0 | 4
3 | 2 | User Profile & Membership | Integration user profile panels, formats and templates | 10 | 4 | 2 | 16 | Assuming there will be different layout and formats for user profile based on roles
2 | 0 | User Profile & Membership | Integrating subscription with user profile with subscription types (Installing modules like we will use MoneySuite and relvent modules as dependencies) | 5 | 0 | 0 | 5 | Assuming there will be memberships defined by admin
3 | 3 | User Profile & Membership | Integrating membership with user profile with membership types - Integrating and configuraing all modules according to user profile as well configuring | 10 | 4 | 3 | 17
2 | 2 | User Profile & Membership | Integrating stripe module with subscriptions and make payment process available. | 4 | 2 | 2 | 8 | Payment will be proceed by Stripe payment gateway
3 | 1 | Team Creation | Team creation - Installing and configuring modules and relevent module and team page screen | 5 | 4 | 0 | 9 | Enabling modules groups module and other related modules. Creating / editing names of group content type, fields required in it.
3 | 1 | Team Creation | Team creation - Adding members and Permission settings on view content etc. | 6 | 4 | 2 | 12
3 | 1 | Team Creation | Team creation - Roles and team member suggestions by admin | 16 | 4 | 3 | 23 | As provided in our architecture document system will recommend user based on matching problem category and his availability set by user himself for joining more teams.
3 | 1 | Team Creation | Team creation - Uploading documents and encryption handling + File constraints | 8 | 0 | 4 | 12
3 | 1 | Team Creation | Documents - Fields, permissions, constraints and integrating within team | 6 | 3 | 1 | 10
4 | 1 | Appointment Creation | Creation of Appointment and fields within groups permissions and constraints | 6 | 4 | 1 | 11
4 | 1 | Appointment Creation | Creation of Appointment - Integration with calandar and shows appointment on calandar | 4 | 4 | 2 | 10
4 | 2 | Task Creation | Creation of Task - making architecture of tasks, Task fields (Installing modules and relevent module according to need) . Actually we will use ubercart and task will be a product and money management feature along with this. | 14 | 4 | 2 | 20 | We will create task as uber cart product. So will module uber cart regarding.
3 | 0 | Task Creation | Task I mean ubercart payment will be charge through stripe online payment gateway | 6 | 0 | 2 | 8
1 | 0 | Task Creation | Creation of Task - Task calandar integration | 3 | 0 | 1 | 4
4 | 2 | Task Creation | Creation of Task - Task calandar integration and user assigning integration and assiging constraints | 9 | 4 | 2 | 15
2 | 0 | Task Creation | Task management - Setting up permissions (Create /Delete / Revise / Assign / Delegate/ Accept / Reject / Approve a task.) | 8 | 0 | 3 | 11
4 | 2 | Task Creation | Task management - Based on field status, Color codes, Priorities, Constraints | 9 | 4 | 2 | 15
4 | 2 | Task Creation | Tasks list for each role | 4 | 4 | 2 | 10
4 | 2 | Task Creation | Tasks list for each user | 4 | 4 | 2 | 10
3 | 1 | Plan Creation | Creation of Plan - Creating master plan that will have the plans, fields, permissions, constraints | 4 | 0 | 1 | 5 | Assuming as per ur clearification under Clarification 4 12/01/2017 -> Clarify the plan & report requirement. That master plan will have plans and plans will have series of tasks
3 | 1 | Plan Creation | Creation of Plan - Creating plan that will have the tasks, fields, permissions, constraints | 5 | 0 | 1 | 6
4 | 2 | Plan Creation | Creation of Plan - Integration with calandar, managing with tasks and plans itself on calandar, Different colors and appearance | 8 | 6 | 3 | 17
4 | 2 | Plan Creation | Creation of view displaying all plan for a specific user | 4 | 4 | 1 | 9
3 | 1 | User Calendar | Creation of Calandar - Installation, configuration, permissions, some relevent modules | 5 | 0 | 1 | 6
4 | 2 | User Calendar | Creation of Calander - User can sync , import , export the calendar with outlook , iCal , Google . | 16 | 0 | 3 | 19 | As we have looked into different module no any module fulfill our complete envirement we have to go with custom coding for achieving the whole requirement.
4 | 3 | User Calendar | User profile - Calander integration with user profile able to pin task/appoint on profile + Permissions to other user in same team able to add appoint request | 10 | 6 | 3 | 19
2 | 1 | Message Board | Message board creation - Installing relevant modules permissions and configurations | 4 | 0 | 1 | 5 | As ther is not much clearification here. We are assuming message board is a funtionality in which users in same group can group chat.
3 | 1 | Message Board | Message board creation - integrating nodejs with server and installing relevent modues | 10 | 0 | 1 | 11
4 | 2 | Message Board | Creating threads under groups | 12 | 8 | 4 | 24
3 | 1 | FAQ | FAQ and relvent like help directory in format and wiki other then support system | 6 | 4 | 1 | 11
4 | 1 | Support System | Creation of Support System - Support Ticketing System module installation, configuration, permissions, constarints | 8 | 0 | 1 | 9
4 | 2 | Support System | Support System - Ticket content type, fields, permissions, constraints, status and feedbacks | 8 | 6 | 2 | 16
3 | 2 | Support System | Tickets views, status and assignment. | 6 | 4 | 2 | 12
2 | 1 | SEO & Analytics | SEO - Installling module and configurations | 4 | 0 | 1 | 5 | We are assuming there will be basic SEO using some module
2 | 1 | SEO & Analytics | Analytics - Installing module and configurations | 3 | 0 | 1 | 4 | We are assuming there will be google analytics which we will configure
3 | 2 | Logging & File Cleaning | Logging - Building user activities logging functionalities on different actions | 6 | 0 | 2 | 8 | Assuming there is not any special screen for this
3 | 1 | Logging & File Cleaning | File cleaning - Integrations with documents, permissions and constraints | 6 | 0 | 1 | 7 | Time estimation is according CleanAV Drupal module and it's features
4 | 2 | Reports | Creating Reports - Presenting progress of tasks in the plan done vs doing+not done | 14 | 6 | 2 | 22 | We are assuming there will be chart of plan done vs doing+not done
4 | 2 | Reports | Creating Reports - Presenting data set provided in format of XML files provided by user | 16 | 4 | 2 | 22 | We are assuming there will be different kind of content as plan user will upload file and will present data in some form
3 | 1 | Reports | Creating Report - Accounting per centric user | 5 | 4 | 1 | 10
3 | 1 | Reports | Creating Report - Who billed and who not | 5 | 4 | 1 | 10
4 | 2 | Search | Search in Content or Users - Creating a view of content with users with respect to roles and respective permissons | 6 | 4 | 2 | 12
4 | 2 | Notification | Notification Mangement | 14 | 0 | 4 | 18 | Admin will be able to set a rule when why what get a notification of change on email. For this we will using Rules module in D7
2 | 2 | Website Theme Design | Wireframe | 0 | 50 | 0 | 50
3 | 2 | Website Theme Design | UI Design | 0 | 70 | 0 | 70
4 | 2 | Website Theme Design | UX Design | 0 | 80 | 0 | 80
3 | 1 | Web Services | Signup (Data Email, firstname, lastname, password, confirm password, phone, documents) | 8 | 0 | 0 | 8 | Assuming sign up with a specific role and describe fields.
3 | 1 | Web Services | Login (Data email/username and password) | 5 | 0 | 0 | 5
3 | 1 | Web Services | Profile editing (It could be documents and questions) | 6 | 0 | 0 | 6
2 | 1 | Web Services | Logout | 2 | 0 | 0 | 2
2 | 1 | Web Services | List of subscription types | 3 | 0 | 0 | 3
2 | 1 | Web Services | List of payment method | 3 | 0 | 0 | 3
3 | 1 | Web Services | List of dynamic questions according to user profile | 6 | 0 | 0 | 6
3 | 1 | Web Services | Answer dynamic question form creation | 6 | 0 | 0 | 6
3 | 1 | Web Services | Answer dynamic question form editing | 3 | 0 | 0 | 3
2 | 1 | Web Services | List of user specific teams | 3 | 0 | 0 | 3
3 | 1 | Web Services | Update team meeting | 4 | 0 | 0 | 4
3 | 1 | Web Services | List of messages (message board) of specific team with respect to user | 6 | 0 | 0 | 6
3 | 1 | Web Services | Write to team message board (message, team id, user id) | 8 | 0 | 0 | 8
2 | 1 | Web Services | Create meeting time (start date, end date, Task name) | 4 | 0 | 0 | 4
2 | 1 | Web Services | List of all user related plans | 3 | 0 | 0 | 3
3 | 1 | Web Services | Update plan task (start date, end date, Task name) | 4 | 0 | 0 | 4
3 | 1 | Web Services | Upload images to server in user folder (Base64 string) | 6 | 0 | 0 | 6
2 | 1 | Web Services | List of done, not done task and in process tasks | 4 | 0 | 0 | 4
4 | 1 | Web Services | Generate push notification to mobile device whenever new team tasks updated | 8 | 0 | 0 | 8
2 | 1 | Web Services | Generate push notification to mobile device whenever new appointment scheduled | 4 | 0 | 0 | 4
2 | 1 | Web Services | Generate push notification to mobile device when documents updated related to task | 3 | 0 | 0 | 3
2 | 1 | Web Services | Generate push notification to mobile device whenever new comments pass on specific task | 3 | 0 | 0 | 3
|  | TOTAL |  | 459 | 322 | 84 | 869 | hours
[7 empty] | 109 | days

## Sheet2
Team | $/H | February | March | April | May | Risk
Prod Owner |  | 0.5 | 0.5 | 0.5 | 0.5
Scrum Master |  | 0.5 | 0.5 | 0.5 | 0.5
Backend Developer |  | 2 | 1 | 0.5 | 0
Front End Developer |  | 1 | 0.5 | 0.25 | 0
QA/Tester |  | 0.5 | 1 | 1 | 0.5
Note on H6: Support only.
Note on H7: Support only.
Note on G9: Support only, not in estimate.
Note on H10: Support only.