## Sheet1
skill | complexity | task_name | subtask_name | Development/Programming | UI Task | QA | Total | Assumptions/Comments
|  | Environment / Drupal Setup / Git Setup (Gitlab or Github) |  | 4 | 0 | 0 | 4
|  | Login form + Complete authentication |  | 0 | 8 | 2 | 10
|  | User Profile panel |  | 4 | 4 | 2 | 10
|  | Create user roles and permission |  | 6 | 0 | 0 | 6
|  | Install require modules/plugins |  | 8 | 0 | 0 | 8
|  | Stripe payment gateway installing module |  | 8 | 0 | 0 | 8
|  | Search in Content or Users - Creating a view of content with users with respect to roles and respective permissons |  | 8 | 4 | 2 | 14
|  | Signup (Data Email, firstname, lastname, password, confirm password, phone) |  | 8 | 4 | 2 | 14
Pages
2 | 1 | Home Page | Top Menu (Home Page) | 4 | 12 | 1 | 17
3 | 2 | Home Page | Slider (Home Page) | 8 | 16 | 1 | 25
2 | 2 | Home Page | Donation form (Home Page) | 8 | 16 | 1 | 25
2 | 2 | Home Page | Act Now Posts (Home Page) | 8 | 16 | 1 | 25
2 | 2 | Home Page | Email Subscription (Home Page) | 4 | 16 | 1 | 21
2 | 1 | Home Page | Our Purpose (Home Page) | 8 | 12 | 0 | 20
3 | 2 | Home Page | Our Most Sustainable Projects Slider (Home Page) | 12 | 24 | 1 | 37
2 | 1 | Home Page | Our Vision (Home Page) | 8 | 8 | 0 | 16
2 | 2 | Home Page | Get Involved (Home Page) | 8 | 18 | 1 | 27
2 | 2 | Home Page | Stories left side section | 8 | 16 | 2 | 26
2 | 2 | Home Page | Most view Stories | 8 | 16 | 1 | 25
2 | 2 | Home Page | Recent Stories | 8 | 16 | 1 | 25
2 | 1 | Home Page | Join US | 4 | 16 | 0 | 20
2 | 1 | Appeals | Donate Now (Appeals) | 6 | 8 | 2 | 16
3 | 2 | Appeals | Donate Cause - Grid form | 16 | 18 | 3 | 37
2 | 1 | Appeals | Other ways you can help (Appeals) | 8 | 12 | 2 | 22
1 | 0 | Appeals | Join us(Appeals) | 4 | 4 | 1 | 9
2 | 1 | What we do | What we do (What we do) | 8 | 8 | 2 | 18
3 | 2 | About us | Vission, Mission, Values, Partner (About us) | 8 | 24 | 0 | 32
2 | 1 | Get Involved | Recommendation - Block | 4 | 12 | 0 | 16
2 | 2 | Get Involved | Become a volunteer - block | 4 | 16 | 1 | 21
2 | 2 | Get Involved | Join a Muntada Aid Event (Get Involved) | 4 | 4 | 1 | 9
3 | 2 | Get Involved | Choose an Event - Grid Events | 16 | 16 | 2 | 34
3 | 1 | Get Involved | Left content with black title | 6 | 16 | 0 | 22
3 | 1 | Get Involved | Right content with Blue title | 6 | 16 | 0 | 22
4 | 1 | Get Involved | Fundraise at your Convenience | 8 | 20 | 0 | 28
2 | 1 | Get Involved | Tools and Tips - Top title and text | 2 | 6 | 0 | 8
4 | 2 | Get Involved | Tools and Tips - View as a block | 8 | 20 | 1 | 29
3 | 1 | Get Involved | Legal Guide - Paragraph | 4 | 6 | 0 | 10
3 | 1 | Get Involved | We are here to help - Paragraph | 8 | 12 | 0 | 20
2 | 1 | Get Involved | BE OUR STAR, Follow us - Paragraph | 4 | 8 | 0 | 12
2 | 2 | Get Involved | Follow us and share | 4 | 4 | 2 | 10
4 | 1 | Media Centre | Media centre top slider | 12 | 12 | 0 | 24
4 | 2 | Media Centre | More news updates from Muntada Aid - Grid news | 8 | 16 | 2 | 26
5 | 1 | Media Centre | Watch how Muntada Aid slider - list news | 16 | 16 | 0 | 32
4 | 1 | Media Centre | More images and videos - Grid image/videos | 8 | 16 | 0 | 24
5 | 2 | Media Centre | Our Twitter Feed slider - Grid status | 16 | 18 | 1 | 35
4 | 1 | News | Left sidebar - Search and filter by category(auto load) | 8 | 12 | 0 | 20
4 | 2 | News | Right sidebar news - Grid news | 12 | 16 | 2 | 30
2 | 0 | Videos | Left sidebar - search | 1 | 1 | 0 | 2
4 | 2 | Videos | Right sidebar videos - Grid videos | 12 | 16 | 2 | 30
2 | 0 | Images | Left sidebar - search | 1 | 1 | 0 | 2
4 | 2 | Images | Right sidebar images - Grid images | 12 | 16 | 2 | 30
4 | 2 | Ramadan 2022 | Appeal in Grid | 12 | 20 | 2 | 34
4 | 1 | Ramadan 2023 | Videos - Grid View (Ramadan 2022) | 12 | 16 | 0 | 28
4 | 1 | Ramadan 2024 | Donate now - blocks | 16 | 18 | 0 | 34
4 | 1 | Ramadan 2025 | Grid - paragraphs | 12 | 20 | 0 | 32
4 | 1 | Ramadan 2026 | Blogs - Grid View | 8 | 20 | 0 | 28
2 | 0 | Content Types | Appeal Content Type | 2 | 0 | 0 | 2
2 | 0 | Content Types | Water Solution - Content Type | 2 | 0 | 0 | 2
2 | 0 | Content Types | Event Content Type | 2 | 0 | 0 | 2
2 | 0 | Content Types | What we do - Content Type | 2 | 0 | 0 | 2
4 | 1 | Content Types | Resources - Content Type | 12 | 0 | 0 | 12
4 | 0 | Content Types | News Content type | 16 | 0 | 0 | 16
4 | 0 | Content Types | Video content Type | 12 | 0 | 0 | 12
4 | 0 | Content Types | Image Gallery - Content Type | 16 | 0 | 0 | 16
3 | 2 | Content Types | Volunteer Form - Webform | 8 | 16 | 0 | 24
Frontend
2 | 1 | Appeal Content Type - Frontend | Donation Form - Right side (Block-1) | 2 | 6 | 2 | 10
2 | 0 | Appeal Content Type - Frontend | Paragraph - image + text - Left side - 1 (Block-1) | 2 | 6 | 0 | 8
2 | 0 | Appeal Content Type - Frontend | Image - Left side - 2 (Block-1) | 2 | 6 | 0 | 8
2 | 1 | Appeal Content Type - Frontend | Text - Left side - 3 (Block-1) | 2 | 6 | 1 | 9
2 | 0 | Appeal Content Type - Frontend | Left-image + Right text - 1 (Block-2) | 2 | 6 | 0 | 8
2 | 0 | Appeal Content Type - Frontend | Right-image + Left text - 2 (Block-2) | 2 | 6 | 0 | 8
3 | 1 | Appeal Content Type - Frontend | Paragraph - image + rating + title + small discription - 1 (Block-3) cart | 4 | 6 | 1 | 11
3 | 0 | Appeal Content Type - Frontend | Paragraph - image + title + price + depth + Beneficiaries + Lifespan + Countries + Learn button - 2 (Block-3) cart | 4 | 6 | 0 | 10
2 | 1 | Appeal Content Type - Frontend | Paragraph - country name + country flag + mission + total no. operations - 3 (Block-3) cart | 2 | 6 | 1 | 9
2 | 0 | Appeal Content Type - Frontend | Paragarph - image + title + small discription - 3 (Block-3) | 2 | 6 | 0 | 8
3 | 0 | Appeal Content Type - Frontend | Paragraph - image + amount + small discription - left side - 1 (Block-4) | 4 | 6 | 0 | 10
2 | 0 | Appeal Content Type - Frontend | Image - right -1 (Block-4) | 2 | 6 | 0 | 8
2 | 1 | Appeal Content Type - Frontend | Paragraph - amount + small discription - left side - 2 (Block - 4) | 2 | 6 | 1 | 9
2 | 0 | Appeal Content Type - Frontend | Paragraph - Heading + small discription - right - 2 (Block - 4) | 2 | 6 | 0 | 8
3 | 0 | Appeal Content Type - Frontend | Slider with multipal images (Block - 5) | 4 | 6 | 0 | 10
4 | 1 | Appeal Content Type - Frontend | Paragrapgh - Title + short disc + price + duration of food use (Block-6) The Power of Your Giving | 4 | 6 | 0 | 10
2 | 1 | Appeal Content Type - Frontend | Paragraph - Videos more than one (Block -7) | 2 | 6 | 0 | 8
2 | 1 | Appeal Content Type - Frontend | Paragraph - more than one image (Block - 8) | 2 | 6 | 0 | 8
2 | 1 | Appeal Content Type - Frontend | Paragraph - left top corner image + title + discription - 1 (Block-9) WHAT HAPPENS NEXT WHEN YOU COMMISSION A WATER WELL | 2 | 6 | 0 | 8
4 | 1 | Appeal Content Type - Frontend | Paragrapgh - center image + title + discription - 2 (Block-9) | 4 | 6 | 0 | 10
4 | 1 | Appeal Content Type - Frontend | Paragraph - image + pdf button (block-10) Funding Pack | 4 | 6 | 0 | 10
4 | 2 | Water Solution - Content Type - Frontend | Donation Form right and left text | 4 | 8 | 4 | 16
4 | 1 | Water Solution - Content Type - Frontend | Tube Wells in Asia + disc | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | SADAQAH JARIYAH - Paragraph | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | Countries | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | How we assign a water well? | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | Photo gallery | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | Latest blogs | 4 | 8 | 0 | 12
4 | 1 | Water Solution - Content Type - Frontend | SUPPORT DROP OF LIFE | 4 | 8 | 0 | 12
4 | 2 | Event Content Type - Frontend | Top content | 4 | 16 | 2 | 22
4 | 1 | Event Content Type - Frontend | Resources | 8 | 8 | 0 | 16
4 | 1 | Event Content Type - Frontend | Related events | 8 | 12 | 0 | 20
2 | 1 | What we do - Content Type - Frontend | Left sidebar - what to do list | 2 | 6 | 3 | 11
2 | 1 | What we do - Content Type - Frontend | Right + title + discription + image gallery | 2 | 6 | 0 | 8
2 | 1 | What we do - Content Type - Frontend | in right - left - Paragraph - Title + disc + Donate button | 2 | 6 | 0 | 8
2 | 1 | What we do - Content Type - Frontend | in right - right - donation form | 2 | 6 | 0 | 8
1 | 0 | Resources - Content Type - Frontend | Resources - Content Type - Frontend | 0 | 16 | 0 | 16
1 | 1 | News Content type - Frontend | News Content type - Frontend | 0 | 16 | 1 | 17
1 | 1 | Video content Type - Frontend | Video content Type - Frontend | 0 | 16 | 1 | 17
1 | 1 | Image Gallery - Content Type - Frontend | Image Gallery - Content Type - Frontend | 0 | 16 | 1 | 17
1 | 2 | Zakat Form - Custom Form within Module | Zakat Form - Custom Form within Module | 0 | 12 | 3 | 15
1 | 2 | Drupal Theme Development | Theming | 0 | 80 | 8 | 88
3 | 0 | Drupal Theme Development | Top hero image with page title area | 4 | 8 | 0 | 12
4 | 1 | Drupal Theme Development | Header | 24 | 24 | 1 | 49
4 | 1 | Drupal Theme Development | Footer | 28 | 24 | 1 | 53
4 | 2 | Additional task | Reporting | 24 | 16 | 4 | 44
4 | 2 | Additional task | Dropdown menu | 24 | 24 | 2 | 50
3 | 2 | Additional task | Gift Aid reporting and feature | 16 | 20 | 4 | 40
|  | Total |  | 744 | 1224 | 88 | 2056 | hours
[7 empty] | 257 | Days
[7 empty] | 12.85 | Months