## Sheet1
skill | complexity | task_name | subtask_name | Backend | Frontend | QA | Total | Assumptions/Comments
1 | 0 | Environment Setup | Git Setup (Gitlab or Github) / Server Setup | 1 | 0 | 0 | 1
3 | 1 | Redesigning | Order page | 16 | 20 | 3 | 39 | In design search form there is a second row where we have Box and button says "OTI", give details related to the field with text "Box". Is search text search? If yes then with what fields we need to match that text. Otherwise explain in details field type and purpose in searching. Cant find this new design: Isnt this "i" icon within each row of the table. As the order list is of all the orders of user's company so putting in a column heading will be bad idea. Add "i" icon to order nr and event name column headings. On hover there should be text. For event show: "Link to event detail page". For order on hover show: "Link to order detail view".
3 | 1 | Redesigning | Completed and Cancelled Orders page | 1 | 1 | 0 | 2
2 | 2 | Redesigning | Order detail view | 0 | 6 | 1 | 7 | Do we need to comment form? Do we need to show Order Activity like currently we have on the page?
3 | 1 | Redesigning | Event listing page | 16 | 20 | 4 | 40 | Need list of column as there is confusion related to this. Can user or company make multiple orders to same one event?
1 | 0 | Redesigning | Archived Event listing page | 1 | 1 | 0 | 2
2 | 1 | Redesigning | Event Detail View | 3 | 3 | 1 | 7
1 | 1 | Redesigning | Salespoint List page | 1 | 1 | 1 | 3
2 | 1 | Redesigning | Adding Salespoint | 2 | 2 | 1 | 5 | Please explain that are we going to add new field Contant name, email and phone. And these are simple user entered field. Plus are we going tor replace these within the old Salespoint View. Do you want to have import form on same page as well?
3 | 2 | Redesigning | Company Detail View | 4 | 4 | 2 | 10
1 | 2 | Redesigning | User Profile View | 0 | 2 | 1 | 3
3 | 1 | Products View | Existing Event | 12 | 10 | 4 | 26 | What products we will show when user selects Products.
3 | 1 | Products View | All Products - Fist page | 12 | 10 | 4 | 26
3 | 1 | Products View | All Products - Event Create | 16 | 10 | 2 | 28 | Under 8.2, I didnt get point 6.
1 | 0 | Products View | All Products - Adding products in cart | 4 | 0 | 0 | 4
2 | 1 | Products View | All Products - Add Salepoints | 4 | 4 | 1 | 9
3 | 1
3 | 1 | Checkout page | Checkout page | 10 | 16 | 2 | 28
2 | 1 | Order Confirmation page | Order Confirmation page | 6 | 8 | 1 | 15
0
1 | 0 | Menu adjustments | Menu adjustments | 1 | 0 | 0 | 1
|  | TOTAL |  | 110 | 118 | 28 | 256 | Hours
[7 empty] | 32 | Days
[7 empty] | 1.6 | Months