## Sheet1
Task | Backend | Frontend | QA | Total | Assumptions/Comments
Products View
Existing Event | 12 | 10 | 4 | 26 | What products we will show when user selects Products.
All Products - Fist page | 12 | 10 | 4 | 26
All Products - Event Create | 16 | 10 | 2 | 28 | Under 8.2, I didnt get point 6.
All Products - Adding products in cart | 4 | 0 | 0 | 4
All Products - Add Salepoints | 4 | 4 | 1 | 9
Checkout page | 10 | 16 | 2 | 28
Order Confirmation page | 6 | 8 | 1 | 15
0
Menu adjustments | 1 | 0 | 0 | 1
0
0
0
TOTAL | 65 | 58 | 14 | 137 | Hours
|  |  |  | 18 | Days
|  |  |  | 0.9 | Months