## Sheet1
| skill | complexity | task_name | subtask_name | Development/ Programming | UI Task | QA | Total | Assumptions/Comments
| 3 | 1 | Site Setup | Environment setup
[5 empty] | 4 |  |  | 4
d | 3 | 1 | Home page | UI/UX |  | 8 |  | 8 | Desigin according to PSD
d | 2 | 0 | Home page | Data entry | 8 | 0 |  | 8 | Text should be provided By Client
d | 3 | 1 | About US | Our history | 5 | 1 |  | 6
| 3 | 1 | About US | Our team | 5 | 2 |  | 7
d | 3 | 1 | About US | Visions and values | 2 | 2 |  | 4
| 3 | 1 | About US | Corporate Citizens | 3 | 2 |  | 5
| 3 | 1 | About US | Community Involvement(based off Seacorp page | 4 | 1 |  | 5
| 3 | 1 | Our busniess | Seacorpimage + minimal text | 4 | 4 |  | 8
| 3 | 1 | Our busniess | Triompohe image+minimal text | 3 | 2 |  | 5
| 2 | 0 | Our busniess | Thompsonimage + minimal text | 2 | 1 |  | 3
| 3 | 1 | Contact Us | Map like on TSL website, layout like Triomphe site | 4 | 1 |  | 5
| 3 | 1 | Footer | Footer | 3 | 2 |  | 5
| NA | 1 | Overall QA of the site | Overall QA of the site |  |  | 12 | 12
d
|  |  | TOTAL |  | 47 | 26 | 12 | 85 | hours
d | [7 empty] | 10.625 | Days
d
d
d
d
d
d
d
d
d
d
d
d
d
d
d
d
d

## Sheet3
Mile Stone #1 Setup and Database Architecture
Website Architecture
Laravel, composer and dependencies installation for latest version
Git
Git repository, members and branch creation.
DB architecture
Entity Relationship diagram
initial migrations
Testing
Rearchitecturing
Retesting
Completion of Mile stone #1 | 71 hrs | 8.8 days
Mile Stone #2 Static Pages development
Theme Integration
Header and Footer with dynamic changes
a. The top most header
i. News
News Listing with pagination
News details page
ii. What is FRP(About Us)
iii. Sales reps Listing with sales rep data entry in DB
iv. Company profile
v. FAQ
vi. Search
Unit Testing & Fixings
b. User Registration with Laravel authentication with editional fields, validations and Captcha
Login
Reset Password
Unit Testing & Fixing
c. Header menu bar
i. Home
*Dynamically load Front Images Slider ,news in left bar
*Product category, industeries served
*Find Reperesentative
ii. Products Listing
Product Detail page
Request a Quote form with email to admin
Specific Fan Pdf downloadable links
Unit Testing & Fixings
Intergration Testing
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #2 | 152 hrs | or 19 days
Mile Stone #3 Resources and Guide
iv. Resources & Guide
Product Catalog & PDF
Product Specifications & PDF
Installation & Maintenance Manuals & PDF
Plasticair Standard Warranty & PDF
Unit Testing & Fixings
Fan Calculators
Calculator 1(Fan Speed Varies With Size & Density Constant)
Calculator 2(Density Varies with Speed Size & Volume Constant)
Calculator 3(Fan Size Varies with Speed & Density Constant)
Calculator 4( Density Calculator (Available in Imperial & Metric Both) )
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Unit / Data Converter
Calculate one by one
Calculate as a whole
Unit Testing & Fixings
Recommendation and development
Revit / DWG Drawings
Revit Drawings
DWG / DXF Drawings
Engineering Resources Guide
Intergration Testing of whole static pages & Fixing
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #3 | 130 hrs | or 16 days
-------Red: Dependent of Admin panel-------
v. Industries Listing
Industries detail page
vi. Applications Listing
application detail page
vii. Contact us Page with Map and Email Integration
Mile Stone #4 Admin Panel Development
2- Admin Dashboard
i) Add/Edit/Delete New Product Categories
Add/Edit/Delete Sub New Product Categories
ii) Add Products
Edit Products
Delete
Show all Products with specific order
Sorting
Unit Testing & Fixings
Recommendation and development
Application
Add/Edit/Delete Sub New application
Sorting Applications
Show all Applicatons with specific order
iii) Edit admin profile / Contact Info
iv) Add/Edit/Delete News
Unit Testing & Fixings
Recommendation and development
v) Industry
Listing
Search
Delete
Add new
Edit
Sorting
Unit Testing & Fixings
Recommendation and development
Slider Images
Listing
Add
Edit
Delete
Sorting
Unit Testing & Fixings
Recommendation and development
vii) Users
a. Manage Professional Users Listing
Edit/Delete
Sorting
Projects
b.Manage Sales representative Users Listing
Edit/Delete
Sorting
Projects
Unit Testing & Fixings
Recommendation and development
viii) Settings
a. Admin setting
Password Change
b. Content pages(Change Static pages content from admin )
------- Dependent of Admin panel-------
v. Industries Listing
Industries detail page
vi. Applications Listing
application detail page
Intergration Testing of whole static pages & Fixing
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #4 | 312hr | or 39 days
Mile Stone #5 Fan Selector FRP -> SWSI Fan Development
3-Fan Selector
1-SWSI Fan
i) FRP Exhaust Fans
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
Unit Testing & Fixings
Recommendation and development
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Consutruction custom options
Unit Testing & Fixings
Recommendation and development
-Quote page layout
.Current Page PDF
.Complete Page PDF
Unit Testing & Fixings
Recommendation and development
-Fan submittal page
.Save Project
.Current page pdf
.Complete PDF
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-Systemfan & its links to other pages
.Google chart curve
.Current Pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #5 | 495.5 hrs | or 61.9 days
Mile Stone #6 Fan Selector FRP -> Inline Fan Development
2 Inline Fan
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
Unit Testing & Fixings
Recommendation and development
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Consutruction custom options
-Quote page layout
.Current Page PDF
Unit Testing & Fixings
Recommendation and development
.Complete PDF
-Fan submittal page
.Save Project
.Current page pdf
Unit Testing & Fixings
Recommendation and development
.Complete PDF
-Systemfancurve & links to other pages
.Google chart curve
.Current Pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #6 | 331 hrs | or 41.3 days
Mile Stone #7 Fan Selector FRP -> Rooftop Fan Development
3 RoofTop Fan
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Consutruction custom options
-Quote page layout
.Current Page PDF
.Complete Page PDF
-Fan submittal page
.Save Project
.Current page pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-Systemfancurve & its links to other pages
.Google chart curve
.Current Pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #7 | 334 hrs | or 41.75 days
Mile Stone #8 Fan Selector Skyplum -> SWSI Induced Flow Fan Development
1-SWSI Induced Flow Fan
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
Unit Testing & Fixings
Recommendation and development
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Unit Testing & Fixings
Recommendation and development
Consutruction custom options
-Quote page layout
.Current Page PDF
.Complete Page PDF
Unit Testing & Fixings
Recommendation and development
-Fan submittal page
.Save Project
.Current page pdf
.Complete pdf
Unit Testing & Fixings
Recommendation and development
-Systemfan & its links to other pages
.Google chart curve
.Current Pdf
.Complete PDF
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-G1 Datasheet
.Google chart curve
.Current pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #8 | 554 hrs | or 69.2 days
Mile Stone #9 Fan Selector Skyplum -> DMF Induced Flow Fan Development
-2 DMF Induced Flow Fan
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Consutruction custom options
-Quote page layout
.Current Page PDF
.Complete PDF
Unit Testing & Fixings
Recommendation and development
-Fan submittal page
.Save Project
.Current page pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-Systemfan & its links to other pages
.Google chart curve
.Current Pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-G1 Datasheet
.Google chart curve
.current pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #9 | 414.5 | or 51.75 days
Mile Stone #10 Fan Selector Skyplum -> SWSI Induced Flow Fan-STL Development
-3 SWSI Induced Flow Fan-STL
a.Fan selection page
b.Form values page
Fans Calculations
*Listed Fans
*Google chart based on selected fan
Unit Testing & Fixings
Recommendation and development
c. User Based flow of pages
*Professional User flow
-Option select page
-Fan submittal page & its links to other pages
.save project
.System fan curve page
.Fanselection form page
*Sales User flow
-Quotation page
-Option select page
Motor options & custom options
Consutruction options
Consutruction custom options
-Quote page layout
.Current Page PDF
.Complete Page PDF
Unit Testing & Fixings
Recommendation and development
-Fan submittal page
.Save Project
.Current page pdf
.Complete PDF
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-Systemfan & its links to other pages
.Google chart curve
.Current Pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Recommendation and development
-G1 Datasheet
.Google chart curve
.Current pdf
.Complete pdf
.DWG downloadable link
.CAD downloadable link
.Revit downloadable link
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Completion of Mile stone #10 | 408 hrs | or 51 days
Mile Stone #11 Project Saving and My Account page Development
4- My Accounts page
i)My profile
*user profile editing
iii)My Projects Listing
Edit
Delete
Unit Testing & Fixings
Acceptence Testing (Plasticair will do that)
Recommendation and development
Website Deployement and Final testing
Completion of Mile stone #11 | 75 hrs | or 9.3 days

## Sheet2
ii) Perchloric Acid Exuast |  |  |  | 0
a.Fan selection page | 14 | 4 | 2 | 20 | 18 text files, 3 drop down, 2 radio buttons, 2 button it contains detail about project, fans detail (there wheel dia,cfm etc…) fan models… and Units imperiral or metric
b.Form values page |  |  |  | 0 | 3button, this page shows the fans based on values entered in Fanslection page and it has also link to other pages and google chart generation as well
Fans Calculations | 24 | 0 | 4 | 28
*Listed Fans | 4 | 4 | 2 | 10
*Google chart based on selected fan | 8 | 2 | 1 | 11
0
0
c. User Based flow of pages | Accomodated in Sales User Flow |  |  | 0
*Professional User flow |  |  |  | 0
-Option select page |  |  |  | 0 | 1 drop down, 1 text field, 3 radio, 6 checkboxes, 1 text area
-Fan submittal page & its links to other pages |  |  |  | 0
.save project |  |  |  | 0
.System fan curve page |  |  |  | 0
.Fanselection form page |  |  |  | 0
0
*Sales User flow |  |  |  | 0
-Quotation page |  |  |  | 0
-Option select page | 4 | 2 | 1 | 7
-Quote page layout |  |  |  | 0
.Current Page | 8 | 5 | 3 | 16
.Complete Page | 16 | 4 | 3 | 23
-Fan submittal page |  |  |  | 0
.Save Project |  |  |  | 0
.Current page pdf | 8 | 5 | 3 | 16
-Systemfan | 24 | 16 | 4 | 44
.Google chart curve | 16 | 6 | 4 | 26
.Current Pdf | 8 | 5 | 3 | 16
Total | 134 | 53 | 30 | 217 | Hours
|  |  |  | 28 | days
2