## Sheet1
Time Estimation for Car Valuation
S No. | Task | Subtasks | Hours
1 | Installing React Application and configuration | 1. Routes implementation, Redux & CSS related components 2. Car valuation Form 3. HTML integration in application as already given | 6
2 | Creating HTML pages | 1. First Page (8 hours) 2. Second, Third, Fourth Pages (8 hours) 3. Sign-up / login Pages (8 hours) | 24
3 | Completing First Page and writing HTML code for second page | 1. Completing React functionality for form posting 2. Writng HTML code for second page | 6
4 | Completing Second page and adding corresponding page functionality in ReactJs | 1. Completing second page with React functionality | 6
5 | Completing Third page and adding corresponding page functionality in ReactJs | 1. Completing third page with React functionality | 6
6 | Completing Fourth page and adding corresponding page functionality in ReactJs | 1. Completing fourth page with React functionality | 6
7 | Creating sign-up and login pages | 1. Creating HTML pages for sign-up/login | 6
8 | Adding react functionality for posting login/signup pages to post corresponding selected option | 1. Redirect user to login form if not logged in or sign up 2. Post require options with login form | 6
9 | Getting all responses by APIs and settings functionalities for corresponding responses according to requirement | 1. Test Responses of APIs 2. Test form posting | 6
10 | Synchronise functionality in given application and test authentication for logged in user | 1. Synchronise car valuation functionality in given application 2. Check authentication for guest user i.e registered and logged in | 12
11 | Test Complete Functionality in given Application with all requirements | 1. Application will be tested with given working functionality | 16
|  | Total Hours: | 100